## Scenario List and Coverage
Module | Total scenario | Automation Test script ID | Done | Can be done | Dynamic completed/not | Not feasible | Priority | Sprint | CR ID | Remarks | Module Name | Done(%)
Indent | Budget Head Functionality for Indent |  | No | Yes | [6 empty] | Indent | 53.4483
Indent | Create an Indent with Limited Tender/Open Tender |  | Yes | Yes | Yes
Indent | Create an Indent with Limited Tender/Open Tender wherein the application doesn't prompt the buyer to select a supplier for Limited Tender. |  | No | Yes | Yes
Indent | Check unique Indent number check organisation wise. |  | No | Yes | Yes
Indent | Ensure mandatory field validation for General Information and other IH and IQ templates, whereby the buyer cannot submit an Indent without completing the required fields. |  | No | Yes | Yes
Indent | Verify the functionality of 'Add supplier', including: 1. inviting suppliers, 2. ensuring all registered suppliers are visible in the supplier list. |  | No | Yes
Indent | Confirm that the buyer can preview the Indent Template from the General Information page. |  | Yes | Yes | Yes
Indent | Data can be uploaded using the Excel upload feature both from the General Information page and from individual QH and QI templates. |  | No | No
Indent | An Indent cannot be submitted without an Item template. |  | No | Yes | Yes
Indent | Data upload using Excel upload from General information page and data upload from individual QH and QI Template wise. |  | No | No
Indent | Check SOR item functionality for Indent module |  | Yes | Yes | No
Indent | Verify the preview of the Indent (Consolidated and Tab-wise) while it's in draft state. |  | Yes | Yes | No
Indent | This functionality is configuration-based, where the JRXML is downloaded when a buyer attempts to open the Indent preview. |  | No | Yes | No |  |  |  |  | configuration driven needs to check
Indent | Verify the functionality for adding and deleting items within the item template while it's in draft state. |  | Yes | Yes | Yes
Indent | Item add and delete functionality in item template in draft state after Recall |  | No | Yes | No
Indent | Check the configuration for User-defined, Predefined, and Not Required Indent settings, where the approval type displayed will depend on the organization's configuration |  | No | Yes | Yes
Indent | Only users with the Indent approval role will be populated in the approver list when initiating the approval flow for the indent module. |  | No | Yes | Yes
Indent | Verify the Activity/Role functionality for Indent: Review Activity/Role details in the approval history of Indent (both from the creator's and approver's perspectives). |  | No | Yes | Yes
Indent | Validate general requirements for Approval type, Minimum Approvers and other details. |  | No | Yes | Yes
Indent | Verify all alerts/messages when submitting an Indent. |  | Yes | Yes | Yes
Indent | Reviewing the Approval History from the perspective of both the Indent creator and approver. |  | Yes | Yes | No
Indent | Verification of Decision Masking based on Role and Activity. |  | No | Yes | Yes
Indent | Verify the aggregation value in the Indent preview and from the approver's perspective. |  | No | Yes | No
Indent | Check all clickable events in Indent pending, completed workflow list. |  | No | Yes | Yes
Indent | Navigate to the pending list page of the Indent workflow from the dashboard |  | No | Yes | Yes
Indent | Switch between grid and list view on the approval pending list page/completed list page. |  | Yes | Yes | No |  |  |  |  | done
Indent | Verification of data in the summary section of the Indent. |  | No | Yes | No
Indent | Verify approver comment section, all clickable event and icons |  | No | Yes | No
Indent | Upload multiple attachments from both local storage and the eBriefcase during the approval workflow. |  | No | Yes | Yes
Indent | Verify the tree and chat elements in the approval history of the Indent. |  | Yes | Yes | No
Indent | Verify the workflow sequence in the new UI within the Indent approval history. |  | No | Yes
Indent | attachment in mail from mail server |  | No | Yes | Yes
Indent | Mark for FRQ form at the creator's end. |  | Yes | Yes | Yes
Indent | Mark for FRQ form at the last approver end |  | Yes | Yes | Yes
Indent | Verify data in the database corresponding to certain actions, such as marking for RFQ and final submission of Indent. |  | No | Yes | No
Indent | Verify the database to ensure that primary keys are not duplicated. |  | Yes | Yes | Yes
Indent | Verify Indent assignment data and perform user and hierarchy checks. |  | No | Yes | Yes
Indent | Verify user and hierarchy assignments for Indent. |  | No | Yes | Yes
Indent | Ensure data accuracy on the Indent assignment page, including reassignment. |  | No | Yes | No
Indent | Revert to the Indent creator and review the reversal history. |  | No | Yes | No
Indent | Examine Indent data post-reversal back to the Indent creator. |  | No | Yes | No
Indent | Verify all functionalities related to Indent to SN creation. |  | No | Yes | Yes
Indent | Return items from RFQ and verify status on an item-wise basis. |  | No | Yes | Yes
Indent | Validate Indent-specific classification. |  | No | Yes | No
Indent | Perform correctly search and sorting on the listing page and workflow list page. |  | No | Yes | Yes
Indent | Ensure proper pagination for Indent list page |  | No | Yes | No
Indent | Indent event under Action Dropdown 1. View Indent 2. Edit Indent |  | Yes | Yes | Yes |  |  |  |  | done
Indent | Action: Clone Indent |  | Yes | Yes | No |  |  |  |  | done
Indent | Action: Delete Indent |  | Yes | Yes | Yes
Indent | Action: Download workflow Report |  | Yes | Yes | No |  |  |  |  | done
Indent | Action: Life Cycle |  | No | Yes | No |  |  |  |  | method created only to verfy life cycle clickable
Indent | Indent Creation through Excel Upload |  | No | No
Indent | Quick Indent |  | Yes | Yes | No |  |  |  |  | only with non sor item
Indent | Creation of a Sanction Note from an Indent |  | No | Yes | Yes
Indent | Split & Marge Indent |  | No | Yes | No
Indent | Release/Return Item |  | No | Yes | No
Indent | Indent Clone |  | Yes | Yes | No
Indent | Revert Back to Indent Creator (After Assignment/Claim) |  | Yes | Yes | Yes
Indent | Clarification/Discussion (Indent Link) |  | No | Yes | Yes |  |  |  |  | handled in production defect
Indent | Clarification/Discussion Report |  | No | Yes | Yes |  |  |  |  | handled in production defect
Indent | Life Cycle Report |  | No | Yes
Indent | Workflow Report |  | No | Yes
Indent | Budget Checking |  | No | Yes
Indent | Indent Predefined workflow |  | Yes | Yes | No
Indent | Check the indent approval process with the least number of approvers==> Happy flow for userdefined workflow. |  | Yes | Yes | Yes
Indent | verify indent details in section wise view |  | Yes | Yes | No
Indent | Make an Indent with Userdefined workflow |  | Yes | Yes | Yes
Indent | Check if the Indent can be forwarded to the next approver. |  | Yes | Yes | Yes
Indent | Check if the Indent can be sent back to the person who previously approved it for review. |  | Yes | Yes | Yes
Indent | Check if the Indent can be sent back to the person who created it for review. |  | Yes | Yes | Yes
Indent | Check if the person who created the Indent can recall it |  | Yes | Yes | Yes
Indent | Check if the person who previously approved the Indent can recall it. |  | Yes | Yes | Yes
Indent | Make sure that an Indent can go through multiple workflows (up to 5) before being approved. |  | Yes | Yes | Yes
Indent | Make sure that an Indent can go through a complex approval process with more than 40 approvers involved. |  | Yes | Yes | Yes
Indent | Make sure comments from each approver are checked in the approval history. |  | Yes | Yes | No
Indent | Confirm that general information messages are validated correctly. |  | Yes | Yes | No
Indent | Check that the details shown in the indent preview are validated accurately. |  | Yes | Yes | No
Indent | Ensure that details from each tab of the indent are validated from the indent approver's perspective. |  | Yes | Yes
Indent | Check the indent approval process without approval workflow==> Happy flow for not required workflow. |  | Yes | Yes | Yes
Indent | Make sure the status of the indent is checked at each step. |  | Yes | Yes | Yes
Indent | Check if the indent is marked for the RFQ process correctly. |  | Yes | Yes | Yes
Indent | Confirm the list of assignments for the indent. |  | Yes | Yes | Yes
Indent | Test the claim feature to ensure it works properly. |  | Yes | Yes | Yes
Indent | Ensure the correct selection of the Tender Template group. |  | Yes | Yes | Yes
Indent | Check the creation of a tender from an indent. |  | Yes | Yes | Yes
Indent | verify indent Delete Feature |  | Yes | Yes | Yes
Indent | Verify Cancel Indent Feature with userdefined workflow |  | Yes | Yes | Yes
Indent | Verify Predefined approval workflow with multiple approvers |  | Yes | Yes | Yes
Indent | Check branching/discussion feature with multiple approvers |  | Yes | Yes | Yes
Indent | Verify mail validations against some events like: Indent creation, Review, approve, recall etc. |  | Yes | Yes | Yes
Indent | validate data in indent preview |  | Yes | Yes | No
Indent | Approver history validation for Indent creator end and indent approver end |  | Yes | Yes | No
Indent | Custom Template Group Support |  | Yes | Yes | No
Indent | Indent creation from UI |  | Yes | Yes | Yes
Indent | Indent creation through Excel Upload |  | No | No
Indent | Quick Indent creation |  | Yes | Yes | [5 empty] | only with non sor item
Indent | parent-child item Support |  | No | Yes | [5 empty] | needs to do
Indent | view/Print Indent |  | Yes | Yes | [5 empty] | done
Indent | Indent approval |  | Yes | Yes | Yes
Indent | view approval history |  | Yes | Yes | Yes
Indent | Clarification/Discussion (Indent link) |  | No | Yes | No
Indent | Clarification/Discussion report |  | No | Yes | No
Indent | Indent cancellation |  | Yes | Yes | Yes
Indent | Delete Draft Indent |  | Yes | Yes | Yes
Indent | Flip Indent to RFx |  | Yes | Yes | Yes
Indent | Flip Indent to Sanction Note |  | No | Yes | Yes
Indent | Split & Merge Indent |  | No | Yes | [5 empty] | functionality not present
Indent | Indent assignment (Self or other user) |  | Yes | Yes | Yes
Indent | Mark for RFQ |  | Yes | Yes | Yes
Indent | Revert Back to Indent creator |  | Yes | Yes
Indent | Release/Return item (RFQ to Indent) |  | No | No | [5 empty] | chapcha handle
Indent | Life Cycle report |  | No | Yes
Indent | workflow report |  | Yes | Yes
Indent | budget Checking |  | No | Yes | [5 empty] | configuration driven needs to check
Indent | Indent Clone |  | Yes | Yes
Indent | Customized email Notification |  | No | Yes
Tender | During tender creation from PR, paste the PR reference number in the tender description. |  | Yes | Yes | Yes
Tender | Handle multiple paths for creating tender from PR. |  | No | Yes | Yes
Tender | Automatically populate POC from PR and Indent based on mapping. |  | Yes | Yes | Yes
Tender | In the Indent section, add supplier tender type. |  | No | Yes | Yes
Tender | Set tender currency |  | Yes | Yes | Yes
Tender | Auto-populate procurement category. |  | No | Yes | Yes
Tender | Add supplier: My supplier. |  | Yes | Yes | Yes
Tender | System-suggested supplier. |  | No | Yes | No
Tender | Category-wise filter under 'My Supplier'. |  | No | Yes | No
Tender | Unregistered functionality. |  | No | Yes | No
Tender | Normal supplier search. |  | Yes | Yes | No
Tender | Association filter under both tabs. |  | No | Yes | Yes
Tender | System-suggested supplier: Data population logic, association. |  | No | Yes | No
Tender | Add and add & close options. |  | Yes | Yes
Tender | Generic points linking Indent like preview, Excel upload. |  | No | No
Tender | Validation points of fixed templates (date template, pre-bid template). |  | No | Yes
Tender | Formula, control, validation check against one template. |  | No | Yes
Tender | Auto-population of tender currency, PAC, tender type, reference number. |  | Yes | Yes
Tender | Data population against previously cancelled tender. |  | No | Yes
Tender | Auto-population of bid part. |  | No | Yes
Tender | Procurement category. |  | No | Yes
Tender | In case of Indent and PR, data auto-population. |  | No | Yes
Tender | One item template data from PR and Indent, other template entered by buyer. |  | No | Yes
Tender | Attachment checking internal, both. |  | No | Yes
Tender | Items should be floated without attachment. |  | No | Yes
Tender | Flow of required attachments. |  | No | Yes
Tender | Default data flow in tender template group. |  | No | Yes
Tender | Role map check. |  | No | Yes
Tender | Parent-child, optional item, SOR. |  | No | Yes
Tender | Item grouping. |  | No | Yes
Tender | Check with maximum item count. |  | Yes | Yes
Tender | Delete feature of fresh tender PR or tender, Indent to Tender. |  | No | Yes
Tender | Add item from PR in draft tender. |  | No | Yes
Tender | Attachment: File type, file size, and configuration. |  | No | Yes
Tender | Date format: Date format check, template field, and list page. |  | No | Yes
Tender | Budget and project flow. |  | No | Yes
Tender | Predefine check as per PAC value. |  | No | Yes
Tender | Validation check in case of bid start/close/open date is over, validation message check. |  | No | Yes
Tender | In case of rate field auction, evaluator verifies and confirms auction bid data. |  | No | Yes
Tender | Except rate field auction, there will be a price breakup where the supplier matches auction bid price. |  | No | Yes
Tender | If it is a calculative field, supplier updates data in dependent fields. |  | No | Yes
Tender | If it is a non-calculative field, data will be populated by default. |  | No | Yes
Tender | Verify price breakup start date and end date. |  | No | Yes
Tender | If the price breakup window is closed, the buyer can extend. |  | No | Yes
Tender | Status of price breakup. |  | No | Yes
Tender | CS verification after auction bid submission and decryption. |  | No | No
Tender | Initiate Tender to Service Now (SN) for predefined, user-defined, and not required workflows. |  | No | Yes
Tender | Amend SN from Tender. |  | No | Yes
Tender | Delete SN from Tender. |  | Yes | Yes
Tender | Cancel SN from Tender. |  | Yes | Yes
Tender | Verify Tender to SN cancellation history. |  | Yes | Yes
Tender | Check all events in Tender to SN list page. |  | No | Yes
Tender | Verify action list of Tender to SN at all stages. |  | No | Yes
Tender | Check all email events of Tender to SN. |  | No | Yes
Tender | Approve or reject Tender to SN from email. |  | No | Yes
Tender | Create PO from Tender to SN. |  | No | Yes
Tender | Integrate Tender to SN. |  | No | Yes
Tender | Select project code from Tender to SN. |  | No | Yes
Tender | Initiate Tender to SN clarification. |  | No | Yes
Tender | Event under Action tab: View Tender |  | No | Yes | Yes
Tender | Event under Action tab: Buyer side tender preview |  | No | Yes | No
Tender | Event under Action tab: Download workflow report |  | No | Yes | No
Tender | Event under Action tab: Evaluation settings |  | Yes | Yes | Yes
Tender | Event under Action tab: Total submitted Bid |  | No | Yes | No
Tender | Event under Action tab: Clone |  | No | Yes | No
Tender | Event under Action tab: Clarification/Discussion |  | No | Yes | No
Tender | Event under Action tab: approval History: Initiate Auction |  | No | Yes | No
Tender | Event under Action tab : Download CS |  | No | No
Tender | Event under Action tab: Print and preview CS |  | No | No
Tender | Event under Action tab: Total submitted Bid |  | No | Yes | No
Tender | Fresh RFQ Creation from Excel Upload |  | No | No
Tender | Quick RFQ |  | No | Yes | No
Tender | Create Differential RFQ |  | No | Yes | No
Tender | Auto RFQ Creation/Publication from PR |  | No | Yes | Yes
Tender | Clone RFQ |  | No | Yes | No
Tender | Initiate Pre-Bid Meeting |  | No | Yes | No
Tender | Return Item |  | No | Yes | No
Tender | Tender Clarification/Discussion |  | No | Yes | No
Tender | Tender Predefined workflow |  | Yes | Yes | No
Tender | Verify tender creation without Not Required approval workflow |  | Yes | Yes | Yes
Tender | Check the Tender approval process with the least number of approvers==> Happy flow for userdefined workflow. |  | Yes | Yes | Yes
Tender | Make an Tender with Userdefined workflow |  | Yes | Yes | Yes
Tender | Check if the Tender can be forwarded to the next approver. |  | Yes | Yes | Yes
Tender | Check if the Tender can be sent back to the person who previously approved it for review. |  | Yes | Yes | Yes
Tender | Check if the Tender can be sent back to the person who created it for review. |  | Yes | Yes | Yes
Tender | Check if the person who created the Indent can recall it |  | Yes | Yes | Yes
Tender | Check if the person who previously approved the Tender can recall it. |  | Yes | Yes | Yes
Tender | Make sure that an Tender can go through multiple workflows (up to 5) before being approved. |  | Yes | Yes | Yes
Tender | Make sure that an Tender can go through a complex approval process with more than 40 approvers involved. |  | Yes | Yes | Yes
Tender | Verify Cancel Tender Feature with userdefined workflow |  | Yes | Yes | Yes
Tender | verify Tender Delete Feature |  | Yes | Yes | Yes
Tender | Verify data validation in tender Side |  | Yes | Yes | No
Tender | Return item to PR (check full consume and partial consume) |  | No | Yes | No
Tender | Return item to Indent (check full consume and partial consume) |  | No | Yes | No
Tender | Verify approver history at Tender creator end. |  | Yes | Yes | No
Tender | Custom Template Support (field, Formula, validation, etc.) |  | No | Yes | No
Tender | multiple Formats (TG) as per different Procurement Type |  | No | Yes | Yes
Tender | fresh RFQ creation from UI |  | Yes | Yes | Yes
Tender | fresh RFQ creation from Excel Upload |  | No | No
Tender | RFQ from Indent |  | Yes | Yes | Yes
Tender | RFQ from PR |  | Yes | Yes | Yes
Tender | Quick RFQ |  | No | Yes | No
Tender | Create Differential RFQ |  | No | Yes | No
Tender | parent-child item Support |  | No | Yes | Yes
Tender | auto RFQ creation/Publication from PR |  | No | Yes | Yes
Tender | Customized bid Part Selection |  | No | Yes | Yes
Tender | - Multiple Tender Type Selection (Open/Limited) |  | Yes | Yes | Yes
Tender | System Suggested supplier Suggestion (Limited Tender) |  | No | Yes | No
Tender | buyer Side Tender preview |  | No | Yes | Yes
Tender | Clone RFQ |  | No | Yes | No
Tender | view/Print RFQ |  | No | Yes | Yes
Tender | view overall/tab wise Tender details |  | No | Yes | No
Tender | Initiate Pre-bid Meeting |  | No | Yes | No
Tender | RFQ Publication approval |  | Yes | Yes | Yes
Tender | Corrigendum creation |  | Yes | Yes | Yes
Tender | Corrigendum approval |  | Yes | Yes | Yes
Tender | RFQ cancellation |  | Yes | Yes | Yes
Tender | Delete Draft RFQ |  | Yes | Yes | Yes
Tender | view approval history |  | Yes | Yes | Yes
Tender | Return item |  | No | Yes
Tender | Tender Clarification/Discussion |  | No | Yes | No
Tender | Customized email Notification |  | No | Yes | Yes
Corrigendum | The user should be able to edit the selected template, while other templates remain unselectable. |  | No | Yes
Corrigendum | The last set of approval flow should automatically populate in the next approval flow (Generic). |  | No | Yes
Corrigendum | The system should check attachments and emails on the mail server (generic), and maintain a history of attachments. |  | No | Yes
Corrigendum | Attachment history should be checked. |  | No | Yes
Corrigendum | Once a buyer initiates a corrigendum against price and recalculated templates, the bid will be deleted. All related functionality needs verification. |  | No | Yes
Corrigendum | Assuming the supplier is listed in the tender, what would they see during bid submission if the buyer initiates a corrigendum against any template? |  | No | Yes
Corrigendum | All emails regarding corrigendum need to be checked. |  | No | Yes
Corrigendum | Check the Tender Corrigendum approval process with the least number of approvers==> Happy flow for userdefined workflow. |  | Yes | Yes
Corrigendum | Check Corrigendum status |  | Yes | Yes
Corrigendum | Check corrigendum History link |  | Yes | Yes
Corrigendum | Validate some part of corrigendum History |  | Yes | Yes
Corrigendum | Validate corrigendum ID |  | Yes | Yes
Corrigendum | Make an Tender Corrigendum with Userdefined workflow |  | Yes | Yes
Corrigendum | Check if the Tender Corrigendum can be forwarded to the next approver. |  | Yes | Yes
Corrigendum | Check if the Tender Corrigendum can be sent back to the person who previously approved it for review. |  | Yes | Yes
Corrigendum | Check if the Tender Corrigendum can be sent back to the person who created it for review. |  | Yes | Yes
Corrigendum | Check if the person who created the Indent can recall it |  | Yes | Yes
Corrigendum | Check if the person who previously approved the Tender Corrigendum can recall it. |  | Yes | Yes
Corrigendum | Make sure that an Tender Corrigendum can go through multiple workflows (up to 5) before being approved. |  | Yes | Yes
Corrigendum | Make sure that an Tender Corrigendum can go through a complex approval process with more than 40 approvers involved. |  | Yes | Yes
Corrigendum | Test item attachment and Technical Corrigendum |  | Yes | Yes
Corrigendum | Discard Draft Corrigendum |  | No | Yes
Bid Submission | Check the publication email for Tender (limited tender). |  | No | Yes
Bid Submission | Verify the open tender visibility in the open area. |  | No | Yes
Bid Submission | Ensure data integrity across all tabs on the Tender list page. |  | No | Yes
Bid Submission | Review filters and actions (ALL) functionality. |  | No | Yes
Bid Submission | Verify the actions related to pre-bid meetings. |  | No | Yes
Bid Submission | Confirm that previous bids are displayed correctly after clicking on a bid from the live tender list page. |  | No | Yes
Bid Submission | Check the functionality for drafting and editing bids (draft bid, fresh bid). |  | Yes | Yes
Bid Submission | Verify draft details in the database. |  | No | Yes
Bid Submission | Check terms and conditions against the master copy. |  | No | Yes
Bid Submission | Ensure correct population of bidding currency. |  | No | Yes
Bid Submission | Test excel upload functionality. |  | No | No
Bid Submission | Verify role mapping. |  | No | Yes
Bid Submission | Check optional item functionality. |  | No | Yes
Bid Submission | Ensure parent-child validation. |  | No | Yes
Bid Submission | Review data across three types of attachments. |  | No | Yes
Bid Submission | Verify formulas. |  | No | Yes
Bid Submission | Test clarification request submission from bid submission page. |  | No | Yes
Bid Submission | Check validation against save and submit. |  | No | Yes
Bid Submission | Confirm email events triggered upon bid submission. |  | No | Yes
Bid Submission | Check entry updates after bid submission. |  | No | Yes
Bid Submission | Test re-bid functionality. |  | No | Yes
Bid Submission | Verify bid withdrawal functionality. |  | No | Yes
Bid Submission | Review all actions on the bid list action page. |  | No | Yes
Bid Submission | Check offer validity during bid submission. |  | No | Yes
Bid Submission | Test filters on the bid submission page. |  | No | Yes
Bid Submission | Ensure full flow functionality for Quick RFQ. |  | No | Yes
Bid Submission | Verify bid preview functionality. |  | No | Yes
Bid Submission | Check optional item handling. |  | No | Yes
Bid Submission | Confirm total submitted bids display correctly at the buyer's end. |  | No | Yes
Bid Submission | Bid Submission From Excel Upload |  | No | No
Bid Submission | Excel Bidding |  | No | No
Bid Submission | Email Bidding |  | No | Yes
Bid Submission | Proxy Bidding |  | No | Yes
Bid Submission | Regret/Decline |  | No | Yes
Bid Submission | Join Pre-Bid Clarification/Discussion |  | No | Yes
Bid Submission | Auto reminder: in case of bid not submitted against a limited tender. |  | No | Yes
Bid Submission | Verify Rebid functionality from submitted bid list. |  | Yes | Yes
Bid Submission | Verify bid number before submission of Rebid and after submission of Rebid |  | Yes | Yes
Bid Submission | Verify Rebid functionality from Live Tender list. |  | Yes | Yes
Bid Submission | Verify all alerts which are related with Rebid functionality. |  | Yes | Yes
Bid Submission | Verify Draft bid functionality from Draft bid list. |  | Yes | Yes
Bid Submission | Verify Draft bid functionality from Live tender list. |  | Yes | Yes
Bid Submission | Verify multiple times bid submission from draft bids |  | Yes | Yes
Bid Submission | Verify bid number before bid submission from draft bid |  | Yes | Yes
Bid Submission | Verify all alerts which are related with draft functionality. |  | Yes | Yes
Bid Submission | Verify Rebid functionality from submitted bid list. |  | Yes | Yes
Bid Submission | Verify supplier could not submit bid again after he has withdrawn his submitted bid |  | Yes | Yes
Bid Submission | Verify alert when supplier has tried to submit bid after bid has been withdrawn. |  | Yes | Yes
Bid Submission | verify data at bidder end |  | Yes | Yes
Bid Submission | bid submission from UI |  | Yes | Yes
Bid Submission | bid submission from Excel Upload |  | No | No
Bid Submission | Excel Bidding |  | No | No
Bid Submission | email Bidding |  | No | Yes
Bid Submission | Proxy Bidding |  | No | Yes
Bid Submission | Draft bid |  | Yes | Yes
Bid Submission | Delete/Edit Draft bid |  | Yes | Yes
Bid Submission | multiple Bidding Currency |  | No | Yes
Bid Submission | item wise Currency During Bidding |  | No | Yes
Bid Submission | Re bid |  | Yes | Yes
Bid Submission | Revised/Impact bid |  | No | Yes
Bid Submission | negotiation/Clarification |  | No | Yes
Bid Submission | Regret/Decline |  | Yes | Yes
Bid Submission | bid Withdraw |  | Yes | Yes
Bid Submission | bid preview |  | Yes | Yes
Bid Submission | Pre-bid Clarification/Discussion |  | No | Yes
Bid Submission | Open Clarification |  | No | Yes
Bid Submission | auto reminder: in case of bid not submitted against a Limited tender. |  | No | Yes
Bid Submission | Customized email Notification |  | No | Yes
Evaluation | Verify decryption functionality with and without an evaluator. |  | No | Yes
Evaluation | Test bid opening options: with and without bid opening. |  | No | Yes
Evaluation | Check decryptor functionality with configuration. |  | No | Yes
Evaluation | Test item-wise or overall flag selection. |  | No | Yes
Evaluation | Verify schedule opening time and validation. |  | No | Yes
Evaluation | Review the dashboard of the decryptor. |  | No | Yes
Evaluation | Check scenarios where TC is decryptor and decryptor flag is off. |  | No | Yes
Evaluation | Review bid decryption page: Check all data elements and actions. |  | No | Yes
Evaluation | Select suppliers and decrypt their information. |  | No | Yes
Evaluation | Verify data and actions after decryption. |  | No | Yes
Evaluation | Test initiating auction before submitting in the last stage. |  | No | Yes
Evaluation | Submit bid on decryption page. |  | No | Yes
Evaluation | Verify all mail events. |  | No | Yes
Evaluation | Test new entry creation in pending tasks: from dashboard and pending tasks. |  | No | Yes
Evaluation | - Verify actions when approver required is "no". |  | No | Yes
Evaluation | Review the Evaluation page of the evaluator. |  | No | Yes
Evaluation | Check colour coding of supplier names based on evaluator actions. |  | No | Yes
Evaluation | Verify decision as masking value. |  | No | Yes
Evaluation | Review all events and actions on the evaluator page. |  | No | Yes
Evaluation | Approve all actions. |  | No | Yes
Evaluation | Test raising Evaluation clarifications. |  | No | Yes
Evaluation | Check bid details and bid preview data: formulas, bid map. |  | No | Yes
Evaluation | Test evaluator visibility based on bid parts. |  | No | Yes
Evaluation | Save overall comments and attachments. |  | No | Yes
Evaluation | Verify approval workflow tree and chat history for all covers. |  | No | Yes
Evaluation | - Approve, reject, negotiate actions (optional, mandatory). |  | No | Yes
Evaluation | Test deletion of bids if negotiation is mandatory and supplier does not participate. |  | No | Yes
Evaluation | Ensure comment is mandatory for rejection of a supplier. |  | No | Yes
Evaluation | Review all buttons in Evaluation settings page. |  | No | Yes
Evaluation | Save initial data and Verify in the database. |  | No | Yes
Evaluation | Save evaluator-specific data. |  | No | Yes
Evaluation | Review bid details: field history, apply to all, filter options against tabular template. |  | No | Yes
Evaluation | Test item assignment: parallel, branching. |  | No | Yes
Evaluation | Verify forwarding of previous evaluator decision based on flags. |  | No | Yes
Evaluation | Verify locking functionality. |  | No | Yes
Evaluation | - Test item-wise evaluation specific to HMEL, fixed fields (Qualification Flag). |  | No | Yes
Evaluation | Ensure if parent is disqualified, all child items are disqualified. |  | No | Yes
Evaluation | Ensure if parent is qualified, at least one child item should be selected. |  | No | Yes
Evaluation | Check the count of participated suppliers. |  | No | Yes
Evaluation | Bid Count Visibility |  | No | Yes
Evaluation | Item Wise Bid Status |  | No | Yes
Evaluation | Bid Decrypter Assignment |  | No | Yes
Evaluation | Evaluator Wise Item Assignment |  | No | Yes
Evaluation | Extension Of Offer Validity |  | No | Yes
Evaluation | Tender Merging |  | No | Yes
Evaluation | Auto Bid Opening |  | No | Yes
Evaluation | Workflow Report |  | No | Yes
Evaluation | All Clarification/Discussion Report |  | No | Yes
Evaluation | Return Items After Tender Completion |  | No | Yes
Evaluation | Check the process of creating a tender from an indent. |  | Yes | Yes
Evaluation | Confirm the process of submitting bids with three suppliers. |  | Yes | Yes
Evaluation | Ensure the proper flow for opening bids. |  | Yes | Yes
Evaluation | Check the decryption feature in both cover stages (decryption flow based on roles has not been addressed yet). |  | Yes | Yes
Evaluation | Make sure the evaluation process works smoothly when only one evaluator is involved. |  | Yes | Yes
Evaluation | Check the evaluation settings to accommodate multiple evaluators. |  | Yes | Yes
Evaluation | Confirm the process of moving the evaluation forward to the next step |  | Yes | Yes
Evaluation | Check the functionality to recall evaluations by the previous evaluator. |  | Yes | Yes
Evaluation | Evaluation Comment validation |  | Yes | Yes
Evaluation | If a supplier is rejected in Cover 1, they should not be visible in Cover 2. |  | No | Yes
Evaluation | Rejected supplier data should not be accessible in Cover 2, nor visible in CS. |  | No | No
Evaluation | for Evaluators, Ensure data saving verification in the database across different versions. |  | No | Yes
Evaluation | Rollback options include closing, reverting to the previous stage, or returning to the last approver. |  | No | Yes
Evaluation | Implement auto-bid opening functionality. |  | No | Yes
Evaluation | bid count visibility |  | No | Yes
Evaluation | item wise bid status |  | No | Yes
Evaluation | bid Decrypter assignment |  | No | Yes
Evaluation | bid opening approval |  | Yes | Yes
Evaluation | bid decryption |  | Yes | Yes
Evaluation | evaluator wise item assignment |  | Yes | Yes
Evaluation | bid Evaluation approval |  | Yes | Yes
Evaluation | Part wise Evaluation |  | Yes | Yes
Evaluation | item wise Evaluation |  | Yes | Yes
Evaluation | overall Evaluation |  | Yes | Yes
Evaluation | extension of Offer Validity |  | No | Yes
Evaluation | Evaluation Clarification/Discussion |  | No | Yes
Evaluation | Tender Merging |  | No | Yes
Evaluation | visibility of all bid Versions |  | No | Yes
Evaluation | auto bid opening |  | No | Yes
Evaluation | Download all bid Attachments (single Click) |  | No | Yes
Evaluation | Customized Comparative Statement |  | No | No
Evaluation | Customized email Notification |  | No | Yes
Evaluation | document Ownership Change |  | No | Yes
Evaluation | Rollback |  | No | Yes
Evaluation | MIS report |  | No | Yes
Evaluation | Life Cycle report |  | No | Yes
Evaluation | Flip to Sanction Note |  | No | Yes
Evaluation | workflow report |  | No | Yes
Evaluation | all Clarification/Discussion report |  | No | Yes
Evaluation | Return items after Tender Completion |  | No | Yes
Evaluation | auto System Check of Offer Validity Expiry |  | No | Yes
Evaluation | supplier legacy code Check (Evaluation stage) |  | No | Yes
Negotiation | Initiate negotiation: include comment and time details. Verify all emails related to negotiation. |  | No | Yes | [5 empty] | done validated mail event-359, 152, validated comment in mail event
Negotiation | Ensure suppliers cannot participate in negotiation before the negotiation start date. |  | No | Yes | [5 empty] | done
Negotiation | Suppliers should not be able to participate after the negotiation close date. |  | No | Yes | [5 empty] | done
Negotiation | Before decryption of negotiation bids, Ensure old data is displayed in bid preview, bid details. |  | No | Yes
Negotiation | Test negotiation time extension functionality. |  | No | Yes | [5 empty] | done
Negotiation | After negotiation submission and decryption, Verify data in CS. |  | No | No
Negotiation | Before decryption of negotiation bids, Ensure old data is displayed in bid preview, bid details, and CS. |  | No | No
Negotiation | Revised/Impact Bid |  | No | Yes
Negotiation | Initiate negotiation in cover1 (technical part) |  | Yes | Yes
Negotiation | Negotiate with all suppliers |  | Yes | Yes
Negotiation | Initiate multiple times negotiation in cover1 |  | Yes | Yes
Negotiation | Reject 1 supplier in cover1 and approve rest two suppliers |  | Yes | Yes
Negotiation | Initiate negotiation in cover2 (Price part) |  | Yes | Yes
Negotiation | Negotiate with all suppliers |  | Yes | Yes
Negotiation | Initiate multiple times negotiation in cover2 |  | Yes | Yes
Negotiation | Reject 1 supplier in cover2 and approve another supplier |  | Yes | Yes
Negotiation | Check evaluation/negotiation state in each steps |  | Yes | Yes
Negotiation | Save data during validating bid details |  | Yes | Yes
Negotiation | Verify the count of negotiation bids. |  | No | Yes | [5 empty] | done
Negotiation | Ensure suppliers can Submit negotiation bids either from the submitted bid tab or the negotiation tab. |  | No | Yes | [5 empty] | done
SN | Perform manual SN operations: predefine |  | No | Yes
SN | Perform manual SN operations: user-defined |  | Yes | Yes | [5 empty] | done
SN | Perform manual SN operations: not required |  | Yes | Yes | [5 empty] | done
SN | Amend manual SN. |  | No | Yes
SN | Delete manual SN. |  | Yes | Yes | [5 empty] | done
SN | Cancel MSN. |  | Yes | Yes | [5 empty] | done
SN | Verify MSN deletion history. |  | Yes | Yes | [5 empty] | done
SN | Verify MSN cancellation history. |  | Yes | Yes | [5 empty] | done
SN | Review all events on the MSN list page. |  | Yes | Yes | [5 empty] | select status varification for fresh,
SN | Check the action list of MSN at all stages. |  | No | Yes
SN | Verify all email events of MSN. |  | Yes | Yes | [5 empty] | approval email validation code:: 197,195
SN | Approve or reject MSN from email. |  | No | Yes
SN | Create purchase orders from MSN. |  | Yes | Yes
SN | Integrate MSN. |  | No | Yes
SN | Select project code from MSN. |  | No | Yes
SN | Initiate MSN clarifications. |  | No | Yes
SN | Convert Tender to SN: predefined, user-defined, not required. |  | No | Yes
SN | Amend SN from Tender. |  | No | Yes
SN | Delete SN from Tender. |  | No | Yes
SN | Cancel SN from Tender. |  | No | Yes
SN | Verify Tender to SN cancellation history. |  | No | Yes
SN | Review all events on the Tender to SN list page. |  | No | Yes
SN | Check the action list of Tender to SN at all stages. |  | No | Yes
SN | Verify all email events of Tender to SN. |  | No | Yes
SN | Approve or reject Tender to SN from email. |  | No | Yes
SN | Create purchase orders from Tender to SN. |  | No | Yes
SN | Integrate Tender to SN. |  | No | Yes
SN | Select project code from Tender to SN. |  | No | Yes
SN | Initiate Tender to SN clarification. |  | No | Yes
SN | Check the SN creation==> Happy flow for not required workflow. |  | Yes | Yes
SN | Check the SN approval workflow with the least number of approvers==> Happy flow for userdefined workflow. |  | Yes | Yes
SN | Check the SN predefined approval workflow with multiple approvers==> Happy flow for predefined workflow. |  | Yes | Yes
SN | verify SN Delete Feature |  | Yes | Yes
SN | Verify Cancel SN Feature with userdefined workflow |  | Yes | Yes
SN | Make an SN with Userdefined workflow |  | Yes | Yes
SN | Check if the SN can be forwarded to the next approver. |  | Yes | Yes
SN | Check if the SN can be sent back to the person who previously approved it for review. |  | Yes | Yes
SN | Check if the SN can be sent back to the person who created it for review. |  | Yes | Yes
SN | Check if the person who created the Indent can recall it |  | Yes | Yes
SN | Check if the person who previously approved the SN can recall it. |  | Yes | Yes
SN | Make sure that an SN can go through multiple workflows (up to 5) before being approved. |  | Yes | Yes
SN | Make sure that an SN can go through a complex approval process with more than 40 approvers involved. |  | Yes | Yes
SN | Check SN status of each stage of SN |  | Yes | Yes
SN | Examine the flow from Indent to SN for a subcritical path, where there is no approval process for the Indent and RFQ module. This process should cover all modules quickly to ensure there are no obstacles in any of them. |  | Yes | Yes
SN | Review the process from Indent to SN for a critical path, where there are no approval steps for the Indent and RFQ sections. This should be done swiftly to ensure there are no issues in any of the modules. |  | Yes | Yes
SN | Verify sanction note Approval process with Team WF |  | Yes | Yes
SN | Verify data at Sanction Note |  | Yes | Yes
SN | Verify Amend SN functionality, where buyer amends quantity and technical details and verify from |  | Yes | Yes
SN | - Integration with ERP (API Based/File Based) |  | Yes | Yes
SN | Customized data Point Support (Integration) |  | Yes | Yes
SN | Custom Template Group Support |  | Yes | Yes
SN | Create Sanction Note from RFQ |  | Yes | Yes
SN | Create Sanction Note from Indent |  | Yes | Yes
SN | Create Sanction Note from PR (WIP) |  | Yes | Yes
SN | manual Sanction |  | Yes | Yes
SN | auto System Check on Sanction Note creation |  | No | Yes
SN | - Item-wise L1 Supplier |  | No | Yes
SN | - Overall L1 Supplier |  | No | Yes
SN | manual Check on Sanction Note creation |  | No | Yes
SN | Allocation of Sanction Note to Consortium supplier |  | No | Yes
SN | supplier legacy code Check |  | No | Yes
SN | view/Print Sanction Note |  | No | Yes
SN | Sanction approval |  | Yes | Yes
SN | Delete Draft Sanction Note |  | Yes | Yes
SN | Cancel Sanction Note |  | Yes | Yes
SN | Sanction Note approval history |  | Yes | Yes
SN | Sanction Note Amendment |  | Yes | Yes
SN | Amend Sanction Note for ERP |  | No | Yes
SN | Custom report Format |  | No | Yes
SN | Download Sanction Note report |  | No | Yes
SN | auto System Check of Offer Validity Expiry |  | No | Yes
SN | Life Cycle report |  | No | Yes
SN | Amendment history |  | Yes | Yes
SN | workflow report |  | No | Yes
SN | Clarification/Discussion |  | No | Yes
SN | Clarification/Discussion report |  | No | Yes
SN | Customized email Notification |  | No | Yes
PO | Verify fresh purchase orders. |  | No | Yes
PO | Verify legacy purchase orders. |  | No | Yes
PO | Validate SN to PO flow. |  | No | Yes
PO | Validate Indent to PO flow. |  | No | Yes
PO | Validate PR to ARC PO. |  | No | Yes
PO | Validate PR to NON ARC PO. |  | No | Yes
PO | Populate data from SN/PR/legacy according to mapping. |  | No | Yes
PO | Check purchase order formula. |  | No | Yes
PO | Verify all data and clickable events, filters at the purchase order list. |  | No | Yes
PO | Verify action lists at all stages of the purchase order. |  | No | Yes
PO | Perform SN to POI operations: predefined, user-defined, not required. |  | No | Yes
PO | Verify all fixed fields on the general information page. |  | No | Yes
PO | Review the middle page of SN and PO for quantity updates and verification. |  | No | Yes
PO | Create multiple purchase orders from a single SN. |  | No | Yes
PO | Amend purchase orders (quantity check with SN). |  | No | Yes
PO | Check acceptance of purchase orders (flag-wise). |  | No | Yes
PO | For legacy POs: stages - Draft, accepted. |  | No | Yes
PO | Download CS report and SN report at PO approver's end. |  | No | No
PO | Manage budget project. |  | No | Yes
PO | Send PO data to client ERP and acknowledge. |  | No | Yes
PO | Close PO if it's in the accepted state. |  | No | Yes
PO | Verify Accept PO functionality. |  | No | Yes
PO | Verify reject PO functionality. |  | No | Yes
PO | Check the status of PO after rejection and acceptance. |  | No | Yes
PO | Verify all action events and clickable events at the supplier end. |  | No | Yes
PO | Check the status of PO after rejection and acceptance at the buyer end. |  | No | Yes
PO | Review parent-child features in SN and PO. |  | No | Yes
PO | Check the PO creation==> Happy flow for not required workflow. |  | Yes | Yes
PO | Check the PO approval workflow with the least number of approvers==> Happy flow for userdefined workflow. |  | Yes | Yes
PO | verify PO Delete Feature |  | Yes | Yes
PO | Verify Cancel PO Feature with userdefined workflow |  | Yes | Yes
PO | Make an PO with Userdefined workflow |  | Yes | Yes
PO | Check if the PO can be forwarded to the next approver. |  | Yes | Yes
PO | Check if the PO can be sent back to the person who previously approved it for review. |  | Yes | Yes
PO | Check if the PO can be sent back to the person who created it for review. |  | Yes | Yes
PO | Check if the person who created the Indent can recall it |  | Yes | Yes
PO | Check if the person who previously approved the PO can recall it. |  | Yes | Yes
PO | Make sure that an PO can go through multiple workflows (up to 5) before being approved. |  | Yes | Yes
PO | Make sure that an PO can go through a complex approval process with more than 40 approvers involved. |  | Yes | Yes
PO | Check PO status of each stage of PO |  | Yes | Yes
PO | Examine the flow from Indent to PO for a subcritical path, where there is no approval process for the Indent and RFQ module. This process should cover all modules quickly to ensure there are no obstacles in any of them. |  | Yes | Yes
PO | Review the process from Indent to PO for a critical path, where there are no approval steps for the Indent and RFQ sections. This should be done swiftly to ensure there are no issues in any of the modules. |  | Yes | Yes
PO | Data validation in PO Creation |  | Yes | Yes
PO | Check Amend PO functionality |  | Yes | Yes
PO | Check Amend PO functionality where buyer unable to amend a PO from a sanction note because submitted item quantity of a PO is higher than SN quantity |  | Yes | Yes
PO | check buyer amends SN and increases SN quantity, now he will get "Issue PO" option |  | Yes | Yes
PO | Check, buyer can now submit draft (amend) PO after increasing SN quantity |  | Yes | Yes
PO | Check release draft PO without approval flow |  | Yes | Yes
PO | Check release draft PO with userdefined workflow |  | Yes | Yes
PO | Verify repeat order functionality with not required approval flow |  | Yes | Yes
PO | Verify repeat order functionality with userdefined approval workflow |  | Yes | Yes
PO | - Integration with ERP Inbound (API Based/File Based) |  | No | Yes
PO | - Integration with ERP Outbound (API Based/File Based) |  | No | Yes
PO | Support for Customized data Points (Integration) |  | No | Yes
PO | Support for Custom Template Groups based on different Procurement Types |  | No | Yes
PO | ARC Management |  | No | Yes
PO | creation of orders from Sanction Notes |  | No | Yes
PO | creation of orders from purchase Requisitions (PR) |  | No | Yes
PO | creation of fresh orders |  | No | Yes
PO | Consortium/Dealer assignment |  | No | Yes
PO | order Release |  | Yes | Yes
PO | order cancellation |  | Yes | Yes
PO | deletion of Draft orders |  | Yes | Yes
PO | Viewing/Printing of orders |  | No | Yes
PO | Custom order Copy in RDF Format |  | No | Yes
PO | order Amendment |  | Yes | Yes
PO | supplier acceptance |  | Yes | Yes
PO | Clarification/Discussion |  | No | Yes
PO | Clarification/Discussion report |  | No | Yes
PO | Life Cycle report |  | No | Yes
PO | order approval |  | Yes | Yes
PO | order approval history |  | Yes | Yes
PO | workflow report |  | No | Yes
PO | Amendment history |  | Yes | Yes
PO | Repeat order |  | Yes | Yes
PO | order auto acceptance |  | No | Yes
PO | supplier Sending Request for order |  | No | Yes
PO | creation of Goods Receipt Note (GRN) from order |  | No | Yes
PO | creation of Advanced Shipping Notice (ASN) from order |  | No | Yes
PO | Offering purchase order Financing to supplier |  | No | Yes
PO | Customized email Notifications |  | No | Yes
ASN | Verify ASN Creation from a sanction Note |  | Yes | Yes
ASN | - Integration with ERP (API Based/File Based) - Outbound |  | No | Yes
ASN | Customized data Point Support (Integration) |  | No | Yes
ASN | Custom Template Group Support |  | No | Yes
ASN | Create Advance Shipment Notice from order |  | Yes | Yes
ASN | Inspection Request from supplier Side |  | No | Yes
ASN | buyer approval |  | No | Yes
ASN | ASN Review |  | No | Yes
ASN | auto ASN Approve |  | No | Yes
ASN | Inspection from buyer Side |  | No | Yes
ASN | view/Print ASN |  | No | Yes
ASN | Invoice Upload from supplier Side |  | No | Yes
ASN | Invoice details |  | No | Yes
ASN | supplier Entering Delivery Tracking details |  | No | Yes
ASN | ASN auto Approve |  | No | Yes
ASN | supplier raising Advance & Freight Invoice |  | No | Yes
ASN | Customized email Notification |  | No | Yes
GRN | Verify approved ASN status |  | Yes | Yes
GRN | Verify approved ASN list page, supplier name and other details |  | Yes | Yes
GRN | Create GP without approval workflow |  | Yes | Yes
GRN | Check GP status in GRN list page |  | Yes | Yes
GRN | Create QC without approval workflow |  | Yes | Yes
GRN | Check QC status in GRN list page |  | Yes | Yes
GRN | Create QV without approval workflow |  | Yes | Yes
GRN | Check QV status in GRN list page |  | Yes | Yes
GRN | Verify approved ASN status |  | Yes | Yes
GRN | Verify approved ASN list page, supplier name and other details |  | Yes | Yes
GRN | Create GP with userdefined approval workflow |  | Yes | Yes
GRN | Check GP status in GRN list page |  | Yes | Yes
GRN | Create QC with userdefined approval workflow |  | Yes | Yes
GRN | Check QC status in GRN list page |  | Yes | Yes
GRN | Create QV with userdefined approval workflow |  | Yes | Yes
GRN | Check QV status in GRN list page |  | Yes | Yes
GRN | Examine the flow from Indent to GRN for a subcritical path, where there is no approval process for the Indent and RFQ module. This process should cover all modules quickly to ensure there are no obstacles in any of them. |  | Yes | Yes
GRN | Review the process from Indent to GRN for a critical path, where there are no approval steps for the Indent and RFQ sections. This should be done swiftly to ensure there are no issues in any of the modules. |  | Yes | Yes
GRN | Direct GRN (Skip ASN) from Order |  | No | Yes
GRN | Create GRN stage using barcode |  | No | Yes
GRN | Mail Intimation to Other GRN Creator |  | No | Yes
GRN | Cancel GRN |  | No | Yes
GRN | - Integration with ERP (API Based/File Based) - Inbound & Outbound Both |  | No | Yes
GRN | Customized data Point Support (Integration) |  | No | Yes
GRN | Custom Template Group Support |  | No | Yes
GRN | Direct Goods Receipt Note (GRN) (Skip ASN) from order |  | No | Yes
GRN | Create GRN from ASN |  | Yes | Yes
GRN | Create GRN stage using barcode (WIP) |  | Yes | Yes
GRN | Multi-Step GRN creation |  | Yes | Yes
GRN | - Gate Entry |  | No | Yes
GRN | - Gate Pass |  | Yes | Yes
GRN | - Inspection |  | No | Yes
GRN | - Quantity Check |  | Yes | Yes
GRN | - Quality Verification |  | Yes | Yes
GRN | - Day Book |  | No | Yes
GRN | - Etc. |  | No | Yes
GRN | GRN approval |  | Yes | Yes
GRN | view approval history |  | Yes | Yes
GRN | Cancel GRN |  | Yes | Yes
GRN | view/Print GRN |  | No | Yes
GRN | email auto reminder |  | No | Yes
GRN | mail Intimation to other GRN Creators |  | No | Yes
GRN | Customized email Notification |  | No | Yes
Notesheet | Notesheet creation without approver |  | Yes | Yes
Notesheet | create Notesheet with reinitiate flow |  | Yes | Yes
Notesheet | create notesheet with user defined approver |  | Yes | Yes
Notesheet | create notesheet with multiple approver |  | Yes | Yes
Notesheet | Cancel Notesheet |  | No | Yes
Notesheet | Delete Draft Notesheet |  | No | Yes
Notesheet | Amendment History |  | No | Yes
Notesheet | Notesheet Report |  | No | Yes
Notesheet | Reinitiate Notesheet |  | No | Yes
PR | Push PR data dynamically and create tender from PR Data. |  | Yes | Yes
PR | include RFQ creator ID in the JSON body. |  | Yes | Yes
PR | include organization hierarchy in the JSON body. |  | Yes | Yes
PR | Omit organization hierarchy and RFQ ID from the JSON body. |  | No | Yes
PR | Verify data properties and validation in JSON. |  | No | Yes
PR | Validate data on the PR list page. |  | No | Yes
PR | Review item view and PR view. |  | No | Yes
PR | Verify all actions available. |  | No | Yes
PR | - Ensure data sorting (expected "Me" comes first). |  | No | Yes
PR | Check data against each column. |  | No | Yes
PR | Test filter, search, and deep search functionalities. |  | No | Yes
PR | Assign and reassign PRs. |  | No | Yes
PR | Show PR documents. |  | No | Yes
PR | Access PR documents. |  | No | Yes
PR | view PR data. |  | No | Yes
PR | Review PR lifecycle. |  | No | Yes
PR | Test claim functionality. |  | No | Yes
PR | Download workflow report. |  | No | Yes
PR | Access ARC information. |  | No | Yes
PR | Issue ARC purchase orders. |  | No | Yes
PR | Issue NON-ARC purchase orders. |  | No | Yes
PR | Create supplier Notifications. |  | No | Yes
PR | Review cancellation details. |  | No | Yes
PR | Review closure details. |  | No | Yes
PR | Verify clickable item count in PR list. |  | No | Yes
PR | Check information under other tabs as per configuration. |  | No | Yes
PR | Review PR state in all tabs. |  | No | Yes
PR | Ensure blue link document numbers are clickable. |  | No | Yes
PR | HMEL specific: when a PO is released with a PR, the PR will be moved to the closed stage. |  | No | Yes
PR | - Integration with ERP (API Based/File Based) |  | No | Yes
PR | Customized data Point Support while PR Import/Integration |  | No | Yes
PR | view & Download Full PR data |  | No | Yes
PR | Split & Merge PR |  | No | Yes
PR | PR auto assignment |  | No | Yes
PR | PR manual assignment |  | No | Yes
PR | PR Re-assignment |  | No | Yes
PR | Flip PR to RFx (Manually) |  | Yes | Yes
PR | Flip PR to RFx (Automatically) |  | No | Yes
PR | Flip PR to Sanction |  | No | Yes
PR | Flip PR to ARC purchase order |  | No | Yes
PR | Flip PR to NON-ARC purchase order |  | No | Yes
PR | Cancel PR (manual) |  | No | Yes
PR | close PR (manual) |  | No | Yes
PR | PR Amendment |  | No | Yes
PR | PR locking & Unlocking |  | No | Yes
PR | Life Cycle report |  | No | Yes
PR | Release item on Tender cancellation |  | No | Yes
PR | Attachment at Header Level |  | No | Yes
PR | Attachment at item Level |  | No | Yes
PR | - Flag Based PR Visibility (Own/All/As per Organization Hierarchy) |  | No | Yes
PR | PR visibility at Header Level & item Level |  | No | Yes
PR | auto closure of PR (if PO released) |  | No | Yes
PR | Customized email Notification |  | No | Yes
Auction/ Direct Auction | Initiate Auction from RFQ |  | No | Yes
Auction/ Direct Auction | Direct Auction (Excel Upload) |  | No | No
Auction/ Direct Auction | Different Auction Types (RA/FA) |  | No | Yes
Auction/ Direct Auction | Customized General Terms & Condition |  | No | Yes
Auction/ Direct Auction | Different Auction Rules ▪ English No Ties ▪ Rank Bidding Dynamic SBD ▪ Rank Bidding Same SBD ▪ Dutch Auction |  | No | Yes
Auction/ Direct Auction | Different Auction Strategy ▪ Normal Item Wise ▪ LOT Item Wise ▪ LOT Item Wise Lumpsum ▪ LOT Consolidated |  | No | Yes
Auction/ Direct Auction | Auction Observation |  | No | Yes
Auction/ Direct Auction | Action Data Back to mjPRO |  | No | Yes
Auction/ Direct Auction | Price Breakup |  | No | Yes
Auction/ Direct Auction | Relaunch |  | No | Yes
Auction/ Direct Auction | Hard Stop |  | No | Yes
Auction/ Direct Auction | Auction Report |  | No | Yes
Auction/ Direct Auction | Bid Trail Report |  | No | Yes
Auction/ Direct Auction | Bid Rejection Report |  | No | Yes
LOA | Custom Template Group Support |  | No | Yes
LOA | Create LOA from Sanction Note |  | No | Yes
LOA | Delete Draft LOA |  | No | Yes
LOA | LOA cancellation |  | No | Yes
LOA | view/Print LOA |  | No | Yes
LOA | Custom report Format |  | No | Yes
LOA | LOA approval |  | No | Yes
LOA | approval history |  | No | Yes
LOA | LOA Amendment |  | No | Yes
LOA | Amendment history |  | No | Yes
LOA | supplier acceptance |  | No | Yes
LOA | Customized email Notification |  | No | Yes
Invoice/Payment | - Integration with ERP (API Based/File Based) - Inbound |  | No | Yes
Invoice/Payment | Customized data Point Support (Integration) |  | No | Yes
Invoice/Payment | Approve Invoice |  | No | Yes
Invoice/Payment | Revert the Invoice Back to supplier |  | No | Yes
Invoice/Payment | Raise Invoice after Goods Receipt Note (GRN) (Actual Invoice not Uploaded in ASN) |  | No | Yes
Invoice/Payment | view/Print Invoice |  | No | Yes
Invoice/Payment | Penalty Deduction During Invoice approval |  | No | Yes
Invoice/Payment | Make Payment |  | No | Yes
Invoice/Payment | - Part Payment |  | No | Yes
Invoice/Payment | - Full Payment |  | No | Yes
Invoice/Payment | Invoice Discounting Facility to supplier (Roadmap) |  | No | Yes
Invoice/Payment | Customized email Notification |  | No | Yes
Supplier Management | Bulk supplier Upload |  | No | Yes
Supplier Management | new supplier Registration |  | No | Yes
Supplier Management | - Supplier Identity Check (GSTIN/PAN/MSME) for Indian Suppliers (WIP) |  | No | Yes
Supplier Management | supplier Registration approval |  | No | Yes
Supplier Management | client specific Template/field Support to Capture supplier Info |  | No | Yes
Supplier Management | De-Activation |  | No | Yes
Supplier Management | Debarment |  | No | Yes
Supplier Management | System Suggested supplier Selection in RFQ |  | No | Yes
Supplier Management | supplier Profile Modification and Re-approval |  | No | Yes
Supplier Management | legacy code Check/Update |  | No | Yes
Supplier Management | supplier Rating |  | No | Yes
Supplier Management | Survey |  | No | Yes
Common features of Approval Workflow | user-defined or DOP-based Pre-defined workflow |  | No | Yes
Common features of Approval Workflow | Sequential, parallel & Team approver Selection |  | Yes | Yes
Common features of Approval Workflow | - Minimum Parallel Approver Selection |  | Yes | Yes
Common features of Approval Workflow | - Coordinator Selection in Parallel Approval |  | Yes | Yes
Common features of Approval Workflow | Review to last approver |  | Yes | Yes
Common features of Approval Workflow | Review to creator |  | Yes | Yes
Common features of Approval Workflow | Recall by Initiator |  | Yes | Yes
Common features of Approval Workflow | Recall by the Approvers |  | Yes | Yes
Common features of Approval Workflow | Forward to Another user (extension of the Existing workflow) |  | Yes | Yes
Common features of Approval Workflow | Role & Activity Selection |  | No | Yes
Common features of Approval Workflow | masking of actions Taken by the approver |  | No | Yes
Common features of Approval Workflow | multiple Level Branching |  | No | Yes
Common features of Approval Workflow | approval view history |  | Yes | Yes
Common features of Approval Workflow | item assignment During Evaluation |  | No | Yes
Common features of Approval Workflow | Automatic approver Population |  | No | Yes
Other features of mjPRO | Customized Template & Template Group creation |  | No | Yes
Other features of mjPRO | multiple MIS report |  | No | Yes
Other features of mjPRO | Budgets Module |  | No | Yes
Other features of mjPRO | EOI Module |  | No | Yes
Other features of mjPRO | LOA |  | No | Yes
Other features of mjPRO | DOP in approval workflow |  | No | Yes
Other features of mjPRO | E-Briefcase |  | No | Yes
Other features of mjPRO | EMD-PBG Tracking |  | No | Yes
Other features of mjPRO | Clarification/Discussion Module |  | No | Yes
Other features of mjPRO | - Internal & External Communication |  | No | Yes
Other features of mjPRO | - Initiate General Clarification/Discussion from: |  | No | Yes
Other features of mjPRO | - Indent |  | No | Yes
Other features of mjPRO | - Tender |  | No | Yes
Other features of mjPRO | - Sanction Note |  | No | Yes
Other features of mjPRO | - Order |  | No | Yes
Other features of mjPRO | - Supplier Registration Approval |  | No | Yes
Other features of mjPRO | - Initiate Pre-Bid Clarification/Discussion |  | No | Yes
Other features of mjPRO | - Initiate Evaluation Clarification/Discussion |  | No | Yes
Other features of mjPRO | - Multiple Channel(s) Creation |  | No | Yes
Other features of mjPRO | - Close Channel |  | No | Yes
Other features of mjPRO | - Delete Draft Channel |  | No | Yes
Other features of mjPRO | - Add User |  | No | Yes
Other features of mjPRO | - Delete User |  | No | Yes
Other features of mjPRO | - Attention Feature |  | No | Yes
Other features of mjPRO | - Mark Admin User |  | No | Yes
Other features of mjPRO | - File Attachment Facility |  | No | Yes
Other features of mjPRO | - Reply & Forward Feature |  | No | Yes
Other features of mjPRO | - Tagging |  | No | Yes
Other features of mjPRO | - Print Clarification/Discussion |  | No | Yes
Other features of mjPRO | - Clarification/Discussion Report |  | No | Yes
Other features of mjPRO | - Customized Email Notification Setup |  | No | Yes
Other features of mjPRO | Standard Documents |  | No | Yes
Other features of mjPRO | RTF Box Facility |  | No | Yes
Other features of mjPRO | Feedback |  | No | Yes
Other features of mjPRO | Customized Unit Upload |  | No | Yes
Other features of mjPRO | Customized Designation Upload |  | No | Yes
Other features of mjPRO | Various Types of organization structure Support |  | No | Yes
Other features of mjPRO | document Owner Change |  | No | Yes
Other features of mjPRO | Configuration of: Date & time Format |  | No | Yes
Other features of mjPRO | item & Category Upload |  | No | Yes
Other features of mjPRO | supplier & Category mapping Upload |  | No | Yes
Other features of mjPRO | Customized email Notification Setup |  | No | Yes
Other features of mjPRO | Warehouse master Upload |  | No | Yes
Other features of mjPRO | PAC visibility flag |  | No | Yes
Other features of mjPRO | Type of Clarification Selection |  | No | Yes
Other features of mjPRO | Customized bid submission Term & Condition |  | No | Yes
Other features of mjPRO | - Mass Communication (Through E-mail) |  | No | Yes
Other features of mjPRO | Customized Logo Upload |  | No | Yes
Other features of mjPRO | Customized Banner Upload |  | No | Yes
Other features of mjPRO | Profile Picture |  | No | Yes
Other features of mjPRO | OTP login (Admin user) |  | No | Yes
Other features of mjPRO | Integration with buyer Organization’s Own AD |  | No | Yes
Other features of mjPRO | Forget user ID & Password |  | No | Yes
Other features of mjPRO | ARC Catalogue Management (buyer Driven) |  | No | Yes
Other features of mjPRO | Analytics |  | No | No